## Phase I (Cohort 5)
CT State Personnel Development Grant (CT SPDG)
2015-2016 Scope and Sequence
Phase I (Cohort 5 - 10-12 Schools)
| September 2015 | October 2015 | November 2015 | December 2015 | January 2016 | February 2016 | March 2016 | April 2016 | May 2016 | June 2016
Off-site Training (6.5) | September 17, 2015 Leadership Launch Four Points Sheraton, Meriden 8:30 am to 3:30 pm District and School Administrators, PBIS Coach, and Literacy Coach | October 1 or 2, 2015 SWIS Training SERC, Middletown 8:30 am - 11:30 am Administrator, PBIS Coach, Data Entry Person(s) |  | December 2, 2015 (Snow Day December 9) School Wide PBIS - Day 2 SERC, Middletown 8:30 am - 3:30pm School Leadership Team | January 12, 2016 (Snow Day January 19) School Wide PBIS - Day 3 SERC, Middletown 8:30 am - 3:30pm School Leadership Team |  | March 1 and 2, 2016 (Snow Days March 8 and 9) Access to Core Literacy Instruction - Day 4 & 5 SERC, Middletown 8:30 am - 3:30 pm School Leadership Team and District LA Coordinator/ Literacy Specialist
October 20, 2015 School-Wide PBIS - Day 1 SERC, Middletown 8:30 am to 3:30 pm School Leadership Team
On-site TA (5.5) | Initial Site Visit Full Day School Leadership Team | Follow-up Technical Assistance Full Day School Leadership Team | Welcoming Walkthrough Half Day School Leadership Team and Family/Community Members | Follow-up Technical Assistance Full Day School Leadership Team |  | Educational Benefit Review Process Full Day School Leadership Team and Special Education Teachers/Case Managers | Follow-up Technical Assistance Full Day School Leadership Team
Data Collection | SPDG Purpose Statement Team Membership Instructional Prac. Inventory Assessment Inventory Decision-Making Inventory Completed by School Administrators and Coaches during Leadership Launch (Due 10/15) | Team Implementation Checklist (TIC) Completed during training by School Leadership Team (Window Open 10/1-10/31) | Strengths and Recommendations Completed by School Leadership Team and Family Community Members (Due 11/30) | Self-Assessment Survey (SAS) Completed on-line by All Staff (Window Open 11/24 - 12/22) | SW-PBIS Artifacts Completed by School Leadership Team and Shared with Staff for Feedback in Preparation for Spring Pilot (Due 1/29) | Practices to Keep/Change Completed by School Leadership Team and Special Education Teachers/Case Managers (Due 2/26) | TBD Completed by School Leadership Team (Due TBD) | Team Implementation Checklist (TIC) Completed on-line by School Leadership Team (Window Open 4/1 - 4/29) | School-wide Evaluation Tool (SET) Half Day | Administrators' Survey Completed by Principal (Window Open 5/30-6/17)
| SRBI Self-Assessment Completed on-line by School Leadership Team prior to Initial Visit (Window Open 9/15-10/15) |  |  |  | Team Implementation Checklist (TIC) Completed by School Leadership Team (Window Open 1/4 - 1/29)
| SPDG Action Plan, SWIS Licensure Agreement, and Stipend Transmittal Form Completed by School Leadership Team and TAs during Initial Site Visit (Due 10/15) | SWIS Data Entered and Monitored by School Leadership Team | SWIS Data Entered and Monitored by School Leadership Team | SWIS Data Entered and Monitored by School Leadership Team | SWIS Data Entered and Monitored by School Leadership Team | SWIS Data Entered and Monitored by School Leadership Team | SWIS Data Entered and Monitored by School Leadership Team | SWIS Data Entered and Monitored by School Leadership Team | SWIS Data Entered and Monitored by School Leadership Team | SWIS Data Entered and Monitored by School Leadership Team
Phase I Descriptions
Leadership Launch | Orientation to SPDG and completion of inventories of current practice
Initial Site Visit | Completion of SRBI Self-Assessment and SPDG Action Plan
SWIS Training | School-based data management and reporting system for discipline referrals; regular data entry, analysis, and sharing with staff is required for annual renewal
Day 1 School-wide PBIS | Establish school-wide expectations, refine office referral form to be compatible with SWIS, receive orientation to Welcoming Walkthrough
TIC | Guides team development, implementation, monitoring, and revision process for building positive school-wide culture
Welcoming Walkthrough | Process used to reflect and take action on how welcoming school is to students and families served
Day 2 School-wide PBIS | Develop PBIS lesson plans and response flow chart
SAS | Examines the current status and need for improvement of three behavior support systems from staff perspective
Day 3 School-wide PBIS | Develop system for recognition and reinforcement and establish implementation plan for intial roll-out in the Spring
Ed Benefit Review Process | Examination of IEPs for alignment of student need with goals & objectives and special education services to ensure student progress
Day 4 & 5 Core Literacy | Universal Design, Access for Els, and Close Reads/Text Dependent Questions
SET | External evaluation of School-wide PBIS, including principal, staff and student interviews as well as tour of school and review of key documents
Follow-up Technical Assistance
All on-site technical assistance (TA) is customized to support the school's application of training content. Dates are determined in collaboration with building principal. The primary focus of TA is to build capacity of the SPDG School Leadership Team to implement the structures and practices needed to sustain a multi-tiered system of support beyond the life of the grant. An electronic portfolio will be stored on-line of all school products/artifacts developed.

## Phase II (Cohort 4)
CT State Personnel Development Grant (SPDG)
2015-2016 Scope and Sequence
Phase II (Cohort 4 - 14 Schools)
| September 2015 | October 2015 | November 2015 | December 2015 | January 2016 | February 2016 | March 2016 | April 2016 | May 2016 | June 2016
Off-site/On-line Training (5) |  | October 27 and 28, 2015 Strategic Decision-Making Day 1 & 2 SERC, Middletown 8:30 am - 3:30 pm School Leadership Team |  |  |  | January 15 to February 26, 2016 Completion of On-line Modules Re: Standards-Based IEPs - Day 3 School Leadership Teams will complete three modules within given timeframe and prior to TA | March 29 and 30, 2016 Supplemental Behavior Supports - Day 4 & 5 SERC, Middletown 8:30 am - 3:30 pm School Leadership Team
On-site TA (5.5) |  | Data Review and Technical Assistance Full Day School Leadership Team | Follow-up Technical Assistance Full Day School Leadership Team |  | Follow-up Technical Assistance Full Day School Leadership Team | Follow-up Technical Assistance Full Day School Leadership Team |  | Follow-up Technical Assistance Full Day School Leadership Team |  | Data Review Half Day School Leadership Team
Data Collection | Literacy Evaluation Tool (LET) Completed on-line by all staff responsible for reading instruction (Window Open 8/17-9/18) | Revised Inventories and Process Map Completed by School Leadership Team and TAs | ECI/EI Data and Stipend Transmittal Form Completed and Submitted by Principal (Due 11/13) | Self-Assessment Survey (SAS) Completed on-line by all staff (Window Open 11/24 - 12/22) | Protocol/Procedures for Intervention Planning and Progress Monitoring Completed by School Leadership Team and Shared with Staff for Feedback in Preparation for Spring Pilot (Due 1/31) | Sample Word Bank and IEP Matrix Completed by School Leadership Team and TAs and Shared with Staff to Support Future IEP Development | Benchmarks of Quality (BOQ) Completed during training by School Leadership Team (Window Open 3/1 - 3/31) | Sample Initial Line of Inquiry and Behavior Support Plan Completed by School Leadership Team and TAs and Shared with Staff for Feedback in Preparation for Fall Implementation (Due 5/31) | School-wide Evaluation Tool (SET) Half Day | ECI/EI Data Completed and Submitted by Administrator (Due 6/30)
|  | Team Implementation Checklist (TIC) Completed on-line by School Leadership Team (Window Open 10/1-10/31) |  |  | Team Implementation Checklist (TIC) Completed on-line by School Leadership Team (Window Open 1/4 - 1/29) |  |  |  |  | Administrators' Survey Completed by Principal (Window Open 5/30-6/17)
| Literacy Data Universal Screen Administered in each grade and Analyzed by School Leadership Team |  |  |  | Literacy Data Universal Screen Administered in each grade and Analyzed by School Leadership Team |  |  |  | Literacy Data Universal Screen Administered in each grade and Analyzed by School Leadership Team
| SWIS Data Entered and Monitored by School Leadership Team | SWIS Data Entered and Monitored by School Leadership Team | SWIS Data Entered and Monitored by School Leadership Team | SWIS Data Entered and Monitored by School Leadership Team | SWIS Data Entered and Monitored by School Leadership Team | SWIS Data Entered and Monitored by School Leadership Team | SWIS Data Entered and Monitored by School Leadership Team | SWIS Data Entered and Monitored by School Leadership Team | SWIS Data Entered and Monitored by School Leadership Team | SWIS Data Entered and Monitored by School Leadership Team
Phase II Descriptions
Data Review | Analysis of disaggregated, universal screening data to identify Tier 1, 2, and 3 practices to replicate and priorities for improvement
Day 1 Strategic Decision-Making | Examine ways to interpret and analyze assessment data and connect the work of all school teams into a cohesive system of decision-making
Day 2 Strategic Decision-Making | Evaluate and refine process for intervention planning and progress monitoring
Day 3 Standards-Based IEPs | Develop and align IEP goals and objectives with CCSS according to feeback from external IEP Rubric Scoring
Days 4 & 5 Supplemental Supports | Establish targeted and intensive behavioral interventions
BOQ | Used by Year 2+teams to identify areas of success, improvement, and may be used to identify model schools
ECI/EI | Student data will be collected by External Evaluator to measure changes in Effectiveness of Core Instruction and Intervention Fall to Spring
Follow-up Technical Assistance
All on-site technical assistance (TA) is customized to support the school's application of training content. Dates are determined in collaboration with building principal. The primary focus of TA is to build capacity of the SPDG School Leadership Team to implement the structures and practices needed to sustain a multi-tiered system of support beyond the life of the grant. An electronic portfolio will be stored on-line of all school products/artifacts developed.

## Phase III (Cohort 3)
CT State Personnel Development Grant (SPDG)
2015-2016 Scope and Sequence
Phase III (Cohort 3 - 21 schools)
| September 2015 | October 2015 | November 2015 | December 2015 | January 2016 | February 2016 | March 2016 | April 2016 | May 2016 | June 2016
Off-site Training (.5) |  | October 1 or 2, 2015 CICO Training SERC, Middletown 12:30 am - 3:30 pm Administrator, PBIS Coach, BEP Coordinator, CICO Facilitator(s)
On-site Training (3.5) |  | Data Review and Technical Assistance Full Day School Leadership Team |  |  | Ed Benefit Review Process Half Day School Leadership Team and Special Education Teachers/Case Managers | Data Review and Technical Assistance Full Day School Leadership Team |  | Welcoming Walkthrough Half Day School Leadership Team, Family and Community Members |  | Data Review Half Day School Leadership Team
| Literacy Data Universal Screen Administered in each grade and Analyzed by School Leadership Team | Team Implementation Checklist (TIC) Completed on-line by School Leadership Team (Window Open 10/1-10/31) | ECI/EI Data and Stipend Transmittal Form Completed and Submitted by Principal (Due 11/13) | Self-Assessment Survey (SAS) Completed on-line by all staff (Window Open 11/24 - 12/22) | Practices to Keep/Change Completed by School Leadership Team and Spec. Ed. Tchrs./Case Managers (Due 1/29) |  | Benchmarks of Quality (BOQ) Completed on-line by School Leadership Team (Window Open 3/1-3/31) | Strengths and Recommendations Completed by Stakeholders Present (Due 4/29) | School-wide Evaluation Tool (SET) 3 hours on-site | ECI/EI Data Completed and Submitted by Principal (Due 6/30)
Data Collection |  |  |  |  | Team Implementation Checklist (TIC) Completed on-line by School Leadership Team (Window Open 1/4 - 1/29) |  |  | Literacy Evaluation Tool (LET) Completed on-line all staff responsible for reading instruction (Window Open 4/1-4/29) | SRBI Self-Assessment Completed on-line by School Leadership Team (Window Open 5/2-5/20) | Administrators' Survey Completed by Principal (Window Open 5/30-6/17)
[5 empty] | Literacy Data Universal Screen Administered in each grade and Analyzed by School Leadership Team |  |  |  | Literacy Data Universal Screen Administered in each grade and analyzed by School Leadership Team
| SWIS Data Entered and Monitored by School Leadership Team | SWIS Data Entered and Monitored by School Leadership Team | SWIS Data Entered and Monitored by School Leadership Team | SWIS Data Entered and Monitored by School Leadership Team | SWIS Data Entered and Monitored by School Leadership Team | SWIS Data Entered and Monitored by School Leadership Team | SWIS Data Entered and Monitored by School Leadership Team | SWIS Data Entered and Monitored by School Leadership Team | SWIS Data Entered and Monitored by School Leadership Team | SWIS Data Entered and Monitored by School Leadership Team
Please refer to Phase I and Phase II for descriptions